## Slide 1
PROJECT PLAN
eCMRs plan
SyteLine - one Change Management Request form on its own table and IDO. Live on TRN; next: production

## Slide 2
Seven milestones to production
The plan at a glance — each phase in order.
1
Scope
Everything the three legacy CMR screens and the SOW need, on one form.
2
Design
New table and IDO ue_ecmrs, form layout, lookups and scripts.
3
Develop
Built on TRN first — never directly in production. Done.
4
Staging
Tested end to end on TRN; exports checked against the repo. Done 2026-09-29.
5
Launch
Same table, IDO and form in production, from the TRN exports. Next.
6
Test
Full checklist passed on TRN; smoke test in production.
7
Optimize
Two weeks of follow-up with Quality, Engineering, Planning, Purchasing, CM.

## Slide 3
Scope
Replace three legacy CMR screens with one form, built on its own table.
The actual phase flow
Phase 0
Requirements: QC_CMRs, Create Change Request, Change Request Mgmt, the SOW
→
Phase A
Table + IDO ue_ecmrs: 76 columns, no Infor objects changed
→
Phase B
Form: eCMRs_v2.XML through FormSync
→
Phase C
Testing on TRN: done 2026-09-29
→
Phase D
Rollout to production

## Slide 4
BRD
Business requirements for the change.
Business requirements
■
One form for everything the three legacy CMR screens hold, created with New
■
Own table and IDO (ue_ecmrs): no dependency on rs_cmr / rs_crcvr
■
Unique CMR number CMR-YYMMDD-HHMMSS, set on New; never repeats
■
Lookups fill descriptions: Item, Next Assy, Vendor, Dept, Work Center, every Reviewer ID
■
Initial Change ticks the right Req checkboxes; Reason / Cause Codes from the QC_MRRs lists
■
Ticking Closed sets Close Date and Closed By
■
No changes to Infor standard objects; Enflite naming (ue_, ENF)
■
Built and tested on TRN first; delivered through FormSync; kept in GitHub (Enflite/eCMRs)

## Slide 5
TRN first, then production
Everything is built and proven on TRN, then pushed to production later.
On TRN
1
Build table and IDO ue_ecmrs
2
Set Inline Lists, Read Only, CmrNum; Check In
3
Import eCMRs_v2.XML through FormSync; test every field
4
Export SQL Columns + IDO Properties as the production source
→
In production
1
Import the same columns and properties from the TRN exports
2
Check In; verify production against TRN with one script
3
Import the same eCMRs_v2.XML through FormSync
4
Smoke test, then hand over to the team

## Slide 6
Design
A new table and IDO — nothing Infor owns is changed.
Table and IDO
Object
Name
Notes
SQL table
ue_ecmrs
76 columns (+7 system). Text columns char(255)
Key
cmr_num
nvarchar, Primary Key, no default
IDO
ue_ecmrs (alias ec)
One property per column; lengths equal SQL
Key property
CmrNum
String, 255, Default Value blank
Lists
Inline Lists
Status, Priority, Initial Change, Dispositions, Reason, Cause
Auto-filled
Read Only cleared
Descriptions, reviewer names, Close Date, Closed By
Every column and property: docs/production-build-sheet.md

## Slide 7
Design
How the form fills things in — all in eCMRs_v2.XML.
Form mechanisms
On the form
Mechanism
CMR Num on New
StdObjectNewCompleted: CMR- + yyMMdd-HHmmss
Item / Next Assy / Vendor → text
DefaultFrom Item(...), VendNum(VendorName)
Dept / Work Center → description
Validators SetPropertyFromList(..., Description)
Reviewer ID → name (×6)
DefaultFrom EmpNum(<name>) on SLEmployees
Initial Change → Req boxes
DefaultFrom Change(ReqCosting, ...)
Closed → date, user
SetCloseInfo + SetClosedBy scripts
Why each one is built this way, and what failed first: docs/troubleshooting.md

## Slide 8
Develop
Build on TRN first — never directly in production.
Actual build steps
■
Create table and IDO ue_ecmrs in Application Studio (project ue_ENF)
■
Import columns and properties in the grids' own CSV format
■
Set Inline Lists, clear Read Only on auto-filled fields, CmrNum String / no default
■
Check In the IDO — edits don't take effect until it is checked in
■
Build the form with tools/apply_form_changes.py; import through FormSync

## Slide 9
Develop
The form is built as XML and imported through FormSync.
Building the form with FormSync
1
Keep the TRN v1 form in GitHub as the original (rollback copy)
2
tools/apply_form_changes.py edits v1 in place into exports/eCMRs_v2.XML (--check)
3
Import eCMRs_v2.XML into TRN through FormSync, at Site scope
4
Use FormSync to bring the same XML to production at Launch

## Slide 10
Staging
Freeze the TRN build and run final validation before production.
Actual staging approach
1
Test every field on TRN — passed 2026-09-29
2
Export SQL Columns + IDO Properties; compare_live_lengths.py: nothing to change
3
make_production_imports.py builds the production files from those exports
4
Team sign-off on TRN

## Slide 11
Launch
Deploy to production.
Production steps
1
Scheduled window; check ue_ecmrs / eCMRs don't exist in production yet
2
New table ue_ecmrs; import exports/production/ue_ecmrs_SqlColumns_import.csv
3
New IDO ue_ecmrs (alias ec); import ue_ecmrs_IdoProperties_import.csv; Check In
4
Export both grids; make_production_imports.py --verify: production matches TRN
5
Import eCMRs_v2.XML through FormSync at Site scope; give users access as on TRN
6
Smoke test: New, lookups, cascade, codes, save twice, Closed
Rollback
■
New form on a new table — take eCMRs off the menu and keep using the legacy CMR screens, which are untouched. No data is lost.

## Slide 12
Test
Run tests to make sure everything looks good.
Actual test list
■
New gives CMR-YYMMDD-HHMMSS; saves work; no duplicate-key error
■
Every lookup fills its description / name; PO Line shows the line number
■
Initial Change ticks the right Req boxes; Reason / Cause codes list
■
Serial # and LOT # list the item's serials / lots; Closed sets date and user
■
Existing records open without errors; team signs off

## Slide 13
Optimize
Two weeks of optimization, working closely with the team.
Actual optimization backlog
■
Track issues from each team using eCMRs; fix on TRN first
■
Decide: Notify, Reported By lookup, Assigned Buyer, Sub Assembly
■
Retire the legacy CMR screens; decide on history migration
■
Update the CMR procedure (QA-300-037); manager approval